## ROADMAP_GANTT
TOOL 4: UPSCALING ROADMAP - eWAsTER Project
EXAMPLE: WEEE BEHAVE Upscaling (Aradippou CY → Italy)
Select Solution: | WEEE BEHAVE (School Campaigns + Family Awareness)
Target Territory: | UCPB Municipalities (Marche Region, Italy)
Lead Partner: | ARADIPPOU Municipality (Cyprus)
Total Budget (€k): | 523
Project Duration (months): | 24
Phase | Activity | Start Month | End Month | Duration (months) | Budget (€k) | Partner
Phase 1 | Stakeholder mapping | 1 | 3 | 3 | 10 | UCPB
Phase 1 | Baseline KPI collection | 1 | 3 | 3 | 15 | ARADIPPOU
Phase 1 | Budget planning & allocation | 1 | 3 | 3 | 25 | MARCHE
Phase 2 | Materials localization (IT language) | 4 | 8 | 5 | 30 | ARADIPPOU
Phase 2 | Trainers training program | 4 | 8 | 5 | 20 | UCPB
Phase 2 | School campaign adaptation | 4 | 11 | 8 | 25 | MARCHE
Phase 2 | Pilot test (2 schools) | 6 | 8 | 3 | 40 | UCPB
Phase 2 | Pilot extension (5 schools) | 9 | 11 | 3 | 60 | ARADIPPOU
Phase 2 | Adjustments based on feedback | 9 | 11 | 3 | 15 | MARCHE
Phase 2 | Materials certification | 10 | 11 | 2 | 20 | UCPB
Phase 3 | Rollout to 20 schools | 12 | 15 | 4 | 80 | ARADIPPOU
Phase 3 | Family awareness campaign | 12 | 18 | 7 | 100 | MARCHE
Phase 3 | WEEE collection (tonnes) | 13 | 18 | 6 | 50 | UCPB
Phase 3 | Monthly progress monitoring | 12 | 18 | 7 | 30 | ARADIPPOU
Phase 3 | Interim reports | 15 | 16 | 2 | 20 | MARCHE
Phase 3 | External audit | 17 | 18 | 2 | 25 | UCPB
Phase 3 | Scaling to +30% schools | 16 | 18 | 3 | 40 | ARADIPPOU
Phase 3 | Final KPI collection | 18 | 18 | 1 | 15 | MARCHE
Phase 4 | Impact evaluation | 19 | 20 | 2 | 15 | UCPB
Phase 4 | LAP endorsement process | 19 | 21 | 3 | 20 | MARCHE
Phase 4 | Exit strategy definition | 20 | 21 | 2 | 10 | ARADIPPOU
Phase 4 | Permanent network setup | 21 | 21 | 1 | 5 | UCPB
Phase 5 | Follow-up Quarter 1 | 22 | 22 | 1 | 8 | ARADIPPOU
Phase 5 | Follow-up Quarter 2 | 23 | 24 | 2 | 7 | MARCHE
Disclaimer: This workbook is provided as an illustrative template for the eWAsTER D.3.4.1 package. The figures, timing, budgets, and performance values shown here are example values intended to demonstrate how the Tool 4 roadmap can be structured and completed. They are not binding targets and should be adapted to the specific territorial, operational, and financial conditions of each implementing partner. The template is designed as a practical starting point for customization rather than as a final project plan.

## BUDGET_CALCULATOR
BUDGET DISTRIBUTION BY PHASE
Total Budget (€k): | 523
Phase | % Budget | Budget (€k) | Budget (€)
Phase 1: Preparation | 10 | 52.3 | 52300
Phase 2: Adaptation | 25 | 130.75 | 130750
Phase 3: Implementation | 40 | 209.2 | 209200
Phase 4: Monitoring | 15 | 78.45 | 78450
Phase 5: Sustainability | 10 | 52.3 | 52300
TOTAL |  | 523 | 523000

## KPI_TRACKER
KPI PERFORMANCE TRACKING - WEEE BEHAVE
KPI note: The KPI values shown in this template are illustrative and are intended to demonstrate the structure, logic, and expected level of detail of the Tool 4 roadmap. They are not binding targets and should be adapted to the specific territorial, operational, and financial conditions of each implementation context.
KPI | Target Year 1 | Target Year 2 | Result Year 1 | Achievement %
Schools Involved | 20 | 50 | 18 | 90
WEEE Tonnes Collected | 5 | 12 | 4.8 | 96
Families Reached | 2000 | 5000 | 1900 | 95
Cost per Citizen (€) | 1 | 0.9 | 1.1 | 82
Notes:
- Achievement % = (Result Year 1 / Target Year 1) × 100
- Green zone: ≥90%, Yellow: 80-89%, Red: <80%

## RISK_MATRIX
RISK ASSESSMENT MATRIX - WEEE BEHAVE
Risk | Probability (1-5) | Impact (1-5) | Score | Mitigation
School resistance to campaigns | 3 | 2 | 6 | Initial pilot with 2 schools
Budget overrun Phase 3 | 2 | 4 | 8 | 20% contingency reserve
Regulatory barriers (data protection) | 4 | 3 | 12 | Pre-approval with authorities
Partner dropout mid-project | 3 | 1 | 3 | Backup partner identified (Regione Marche)
Low family participation rate | 3 | 3 | 9 | Incentive mechanisms + competitions
WEEE collection target not met | 2 | 3 | 6 | Alternative collection channels
Risk Priority:
Score 10-15: High priority (immediate action)
Score 5-9: Medium priority (monitoring)
Score 1-4: Low priority (routine management)

## PARTNER_ROLES
PARTNER ROLES & BUDGET - WEEE BEHAVE
Partner | Role | WP | Budget (€k) | Contact
ARADIPPOU Municipality (CY) | Solution Leader | WP1-WP5 | 220 | michael.panayiotis@aradippou.cy
UCPB - Unione Pian Bruscolo (IT) | Local Technical Partner | WP2-WP3 | 153 | ucpb@piandelbrus.it
Regione Marche (IT) | Policy Partner | WP3-WP4 | 150 | lorenzo.federiconi@regione.marche.it
TOTAL |  |  | 523
Partner Roles Explanation:
Solution Leader: Brings tested solution from pilot (Aradippou CY)
Local Technical Partner: Implements in new territory (UCPB IT)
Policy Partner: Ensures LAP integration (Regione Marche IT)

## CAPACITY_CHECKLIST
MINIMUM CAPACITY REQUIREMENTS (per role)
Solution: BEHAVE
Role | Organization Type | Minimum Capacity | Training Hours | Tools Provided
Project Coordinator | Municipality/Region | 1 FTE (full-time) | 20 | Excel template + Solution Sheet
Local Liaison | Waste Management | 0.5 FTE | 12 | Campaign materials + stakeholder list
Technical Expert | NGO/Consultant | Part-time (10h/week) | 16 | KPI dashboard + monitoring tools
Policy Officer | Regional Authority | Part-time (5h/week) | 8 | LAP integration guide
Communication Officer | Communications Dept | Part-time (3h/week) | 4 | Social media templates
TOTAL TRAINING HOURS |  |  | 0
Notes:
• FTE = Full Time Equivalent. Adjust capacity based on territory size (small municipality: -20%).
• Training includes online modules + 1-day workshop. Tools downloadable from eWAsTER platform.
• Minimum total capacity: 2.8 FTE + part-time support (3 roles).