## ROADMAP_GANTT
TOOL 4: UPSCALING ROADMAP - eWAsTER Project
EXAMPLE: 0WEEE PROCURE Upscaling (NEUM BA → New Euro-MED Authorities)
Select Solution: | 0WEEE PROCURE (Green Public Procurement)
Target Territory: | New municipalities in Greece, Italy, Spain
Lead Partner: | Municipality of NEUM (Bosnia & Herzegovina)
Total Budget (€k): | 380
Project Duration (months): | 24
Phase | Activity | Start Month | End Month | Duration (months) | Budget (€k) | Partner
Phase 1 | GPP regulatory mapping | 1 | 3 | 3 | 15 | NEUM
Phase 1 | Baseline procurement analysis | 1 | 3 | 3 | 20 | Partner A
Phase 1 | Stakeholder engagement plan | 2 | 3 | 2 | 10 | Partner B
Phase 2 | GPP criteria development (WEEE) | 4 | 7 | 4 | 35 | NEUM
Phase 2 | Procurement training program | 4 | 8 | 5 | 25 | Partner A
Phase 2 | Pilot tender design (3 entities) | 6 | 9 | 4 | 30 | Partner B
Phase 2 | Legal compliance check | 8 | 10 | 3 | 20 | NEUM
Phase 2 | Market consultation | 9 | 11 | 3 | 15 | Partner A
Phase 3 | Launch 10 green tenders | 12 | 15 | 4 | 60 | Partner B
Phase 3 | Supplier engagement | 12 | 17 | 6 | 40 | NEUM
Phase 3 | Monitoring & support | 13 | 18 | 6 | 30 | Partner A
Phase 3 | Scale to 25 tenders | 16 | 18 | 3 | 45 | Partner B
Phase 4 | Impact assessment | 19 | 20 | 2 | 20 | NEUM
Phase 4 | Cost-benefit analysis | 19 | 21 | 3 | 15 | Partner A
Phase 4 | Best practices documentation | 20 | 21 | 2 | 10 | Partner B
Phase 5 | LAP integration | 22 | 23 | 2 | 15 | NEUM
Phase 5 | Replication toolkit | 22 | 24 | 3 | 10 | Partner A
Disclaimer: This workbook is provided as an illustrative template for the eWAsTER D.3.4.1 package. The figures, timing, budgets, and performance values shown here are example values intended to demonstrate how the Tool 4 roadmap can be structured and completed. They are not binding targets and should be adapted to the specific territorial, operational, and financial conditions of each implementing partner. The template is designed as a practical starting point for customization rather than as a final project plan.

## BUDGET_CALCULATOR
BUDGET DISTRIBUTION BY PHASE
Total Budget (€k): | 380
Phase | % Budget | Budget (€k) | Budget (€)
Phase 1: Preparation | 12 | 45.6 | 45600
Phase 2: Adaptation | 33 | 125.4 | 125400
Phase 3: Implementation | 40 | 152 | 152000
Phase 4: Monitoring | 10 | 38 | 38000
Phase 5: Sustainability | 5 | 19 | 19000
TOTAL |  | 380 | 380000

## KPI_TRACKER
KPI PERFORMANCE TRACKING - 0WEEE PROCURE
KPI note: The KPI values shown in this template are illustrative and are intended to demonstrate the structure, logic, and expected level of detail of the Tool 4 roadmap. They are not binding targets and should be adapted to the specific territorial, operational, and financial conditions of each implementation context.
KPI | Target Year 1 | Target Year 2 | Result Year 1 | Achievement %
Public Entities Engaged | 15 | 30 | 13 | 87
Green Tenders Launched | 10 | 25 | 9 | 90
GPP Value (€k) | 150 | 400 | 138 | 92
WEEE Properly Managed (tonnes) | 3.5 | 8 | 3.2 | 91

## RISK_MATRIX
RISK ASSESSMENT MATRIX - 0WEEE PROCURE
Risk | Probability (1-5) | Impact (1-5) | Score | Mitigation
Procurement law conflicts | 4 | 4 | 16 | Legal pre-assessment + expert consultation
Low supplier response | 3 | 3 | 9 | Market consultation + capacity building
Budget constraints entities | 3 | 2 | 6 | Cost-neutral GPP criteria focus
Political resistance | 2 | 3 | 6 | High-level endorsement from mayors
Complex administrative procedures | 3 | 2 | 6 | Simplified tender templates

## PARTNER_ROLES
PARTNER ROLES & BUDGET - 0WEEE PROCURE
Partner | Role | WP | Budget (€k) | Contact
Municipality of NEUM (BA) | Solution Leader | WP1-WP5 | 160 | sladana.masla@neum.ba
Partner Municipality A (GR/IT/ES) | Local Implementation | WP2-WP3 | 120 | partnerA@municipality.xy
Partner Municipality B (GR/IT/ES) | Scaling Partner | WP3-WP4 | 100 | partnerB@municipality.xy
TOTAL |  |  | 380

## CAPACITY_CHECKLIST
MINIMUM CAPACITY REQUIREMENTS (per role)
Solution: PROCURE
Role | Organization Type | Minimum Capacity | Training Hours | Tools Provided
Project Coordinator | Municipality/Region | 1 FTE (full-time) | 20 | Excel template + Solution Sheet
Local Liaison | Waste Management | 0.5 FTE | 12 | Campaign materials + stakeholder list
Technical Expert | NGO/Consultant | Part-time (10h/week) | 16 | KPI dashboard + monitoring tools
Policy Officer | Regional Authority | Part-time (5h/week) | 8 | LAP integration guide
Communication Officer | Communications Dept | Part-time (3h/week) | 4 | Social media templates
TOTAL TRAINING HOURS |  |  | 0
Notes:
• FTE = Full Time Equivalent. Adjust capacity based on territory size (small municipality: -20%).
• Training includes online modules + 1-day workshop. Tools downloadable from eWAsTER platform.
• Minimum total capacity: 2.8 FTE + part-time support (3 roles).