## ROADMAP_GANTT
TOOL 4: UPSCALING ROADMAP - eWAsTER Project
EXAMPLE: WEEE REUSE Upscaling (LINK BA → Social Enterprises Euro-MED)
Select Solution: | WEEE REUSE (Repair Cafés + Vulnerable Employment)
Target Territory: | New social enterprises in Slovenia, Cyprus, Portugal
Lead Partner: | LINK Entrepreneurial Center (Bosnia & Herzegovina)
Total Budget (€k): | 420
Project Duration (months): | 24
Phase | Activity | Start Month | End Month | Duration (months) | Budget (€k) | Partner
Phase 1 | Social enterprise mapping | 1 | 3 | 3 | 12 | LINK
Phase 1 | Baseline repair capacity | 1 | 3 | 3 | 18 | Partner A
Phase 1 | Vulnerable groups identification | 2 | 3 | 2 | 15 | Partner B
Phase 2 | Repair training program design | 4 | 7 | 4 | 30 | LINK
Phase 2 | Trainer training (TOT) | 4 | 8 | 5 | 25 | Partner A
Phase 2 | Pilot repair café setup (3 locations) | 6 | 10 | 5 | 45 | Partner B
Phase 2 | Tools & equipment procurement | 7 | 9 | 3 | 35 | LINK
Phase 2 | Quality standards development | 9 | 11 | 3 | 20 | Partner A
Phase 3 | Rollout 12 repair cafés | 12 | 16 | 5 | 70 | Partner B
Phase 3 | Vulnerable employment integration | 12 | 18 | 7 | 50 | LINK
Phase 3 | WEEE collection partnerships | 13 | 17 | 5 | 35 | Partner A
Phase 3 | Marketing & awareness campaign | 14 | 18 | 5 | 30 | Partner B
Phase 3 | Scale to 25 repair cafés | 17 | 18 | 2 | 40 | LINK
Phase 4 | Impact assessment (social + env) | 19 | 21 | 3 | 25 | Partner A
Phase 4 | Business model sustainability | 19 | 21 | 3 | 20 | Partner B
Phase 4 | Certification process | 20 | 21 | 2 | 15 | LINK
Phase 5 | Network federation setup | 22 | 23 | 2 | 18 | Partner A
Phase 5 | Long-term funding strategy | 22 | 24 | 3 | 12 | Partner B
Disclaimer: This workbook is provided as an illustrative template for the eWAsTER D.3.4.1 package. The figures, timing, budgets, and performance values shown here are example values intended to demonstrate how the Tool 4 roadmap can be structured and completed. They are not binding targets and should be adapted to the specific territorial, operational, and financial conditions of each implementing partner. The template is designed as a practical starting point for customization rather than as a final project plan.

## BUDGET_CALCULATOR
BUDGET DISTRIBUTION BY PHASE
Total Budget (€k): | 420
Phase | % Budget | Budget (€k) | Budget (€)
Phase 1: Preparation | 11 | 46.2 | 46200
Phase 2: Adaptation | 30 | 126 | 126000
Phase 3: Implementation | 45 | 189 | 189000
Phase 4: Monitoring | 10 | 42 | 42000
Phase 5: Sustainability | 4 | 16.8 | 16800
TOTAL |  | 420 | 420000

## KPI_TRACKER
KPI PERFORMANCE TRACKING - WEEE REUSE
KPI note: The KPI values shown in this template are illustrative and are intended to demonstrate the structure, logic, and expected level of detail of the Tool 4 roadmap. They are not binding targets and should be adapted to the specific territorial, operational, and financial conditions of each implementation context.
KPI | Target Year 1 | Target Year 2 | Result Year 1 | Achievement %
Repair Cafés Established | 12 | 25 | 11 | 92
Devices Repaired | 500 | 1200 | 480 | 96
Kg WEEE Reused | 1500 | 3500 | 1420 | 95
Vulnerable Jobs Created | 25 | 60 | 23 | 92
Cost per Device Repaired (€) | 15 | 12 | 16 | 94

## RISK_MATRIX
RISK ASSESSMENT MATRIX - WEEE REUSE
Risk | Probability (1-5) | Impact (1-5) | Score | Mitigation
Low device donations | 4 | 3 | 12 | WEEE collection partnerships + campaigns
Trainee dropout rate | 3 | 2 | 6 | Incentive programs + certifications
Quality control issues | 3 | 3 | 9 | Standardized testing protocols
Market competition (new devices) | 2 | 2 | 4 | Focus on affordability + sustainability
Funding sustainability post-project | 3 | 4 | 12 | Revenue model + social enterprise support
Legal barriers (liability) | 2 | 3 | 6 | Insurance + compliance framework

## PARTNER_ROLES
PARTNER ROLES & BUDGET - WEEE REUSE
Partner | Role | WP | Budget (€k) | Contact
LINK Entrepreneurial Center (BA) | Solution Leader | WP1-WP5 | 180 | majda.penava@link.ba
Social Enterprise Network A (SI/CY/PT) | Local Implementation | WP2-WP3 | 140 | partnerA@socialent.xy
Social Enterprise Network B (SI/CY/PT) | Scaling Partner | WP3-WP4 | 100 | partnerB@socialent.xy
TOTAL |  |  | 420

## CAPACITY_CHECKLIST
MINIMUM CAPACITY REQUIREMENTS (per role)
Solution: REUSE
Role | Organization Type | Minimum Capacity | Training Hours | Tools Provided
Project Coordinator | Municipality/Region | 1 FTE (full-time) | 20 | Excel template + Solution Sheet
Local Liaison | Waste Management | 0.5 FTE | 12 | Campaign materials + stakeholder list
Technical Expert | NGO/Consultant | Part-time (10h/week) | 16 | KPI dashboard + monitoring tools
Policy Officer | Regional Authority | Part-time (5h/week) | 8 | LAP integration guide
Communication Officer | Communications Dept | Part-time (3h/week) | 4 | Social media templates
TOTAL TRAINING HOURS |  |  | 0
Notes:
• FTE = Full Time Equivalent. Adjust capacity based on territory size (small municipality: -20%).
• Training includes online modules + 1-day workshop. Tools downloadable from eWAsTER platform.
• Minimum total capacity: 2.8 FTE + part-time support (3 roles).