# eWAsTER Solution Sheet

## D.3.4.1 Transfer Package Component

Designed for: Solution Leaders (WEEE BEHAVE, 0WEEE PROCURE, WEEE REUSE)

Maximum time investment: 2 hours per solution

Goal: Data autonomy (no PP meetings required) and sufficient coverage for the transferability matrix and roadmap

Output quality: 3-page structured input for UCPB integration into D.3.4.1

## SECTION 1: DOCUMENT INFORMATION

Solution Name:

WEEE REUSE

Solution Leader (Primary Coordinator):

Majda Penava, LINK

Number of Participating Territories:

2 countries

Participating Partners:

LINK — Bosnia and Herzegovina

ORZ — Slovenia

Sheet Version & Status:

X v1.0 Draft ☐ v2.0 CO Review ☐ v3.0 Approved

Date Completed:

22.05.2026

WP2 Final Report Reference:

WEEE REUSE WP2 Final Report, 06 April 2026

## SECTION 2: EXECUTIVE SUMMARY (300 words max)

### 2.1 Problem Addressed

The WEEE REUSE pilot addresses the underdeveloped role of reuse within existing e-waste management systems in the pilot territories, where current frameworks are primarily focused on collection, recycling, and treatment rather than on extending product lifecycles. Despite increasing volumes of electronic waste, reuse and preparation-for-reuse remain marginal activities, particularly in emerging systems such as Bosnia and Herzegovina, where reuse practices are still at an early stage and lack formal integration into policy and operational frameworks.

### 2.2 Core Innovation

The WEEE REUSE solution is innovative because it integrates circular economy practices with social inclusion, combining reuse activities such as repair, refurbishment, and repurposing with tailored employment models for vulnerable groups. Unlike traditional WEEE systems focused mainly on collection and recycling, this approach introduces reuse as a complementary and value-generating layer, including creative repurposing and safe alternatives such as deep-cleaning processes.

The level of innovation can be considered moderate to high, as it builds on existing waste management structures while addressing a critical gap: the lack of operational and policy integration of reuse. It does so by linking businesses, social enterprises, and system operators into a functional reuse ecosystem.

### 2.3 Key WP2 Results

WEEE collected and processed: 24,486 kg of e-waste (24,019 items) collected across Bosnia and Herzegovina and Slovenia, demonstrating strong engagement and operational feasibility.

Stakeholder participation: 20 organizations involved (11 in Slovenia, 9 in Bosnia and Herzegovina) across multiple sectors, including social enterprises, SMEs, NGOs, and public utilities.

Employment and social impact: 18 jobs created for vulnerable groups (14 preserved or created by stakeholders in Slovenia, 4 in Bosnia and Herzegovina), with additional existing jobs supported and stabilized.

Economic value generated: More than EUR 4,400 in revenue generated in Bosnia and Herzegovina from reuse-based activities, confirming the viability of small-scale reuse business models.

System-level impact and scalability: Reuse practices were tested across two different system contexts, one emerging and one mature, with Slovenia achieving more than 20 tonnes processed within existing infrastructure and both territories confirming readiness for further scaling under enabling policy conditions.

### 2.4 Transnational Potential (2-3 sentences)

The WEEE REUSE solution has strong transnational potential because it builds on existing waste management systems, local businesses, and social economy actors that are present across Euro-MED territories. The pilot demonstrated that reuse can be adapted to both emerging systems, where capacity building is the priority, and mature systems, where integration and optimization are the main drivers.

Transfer is feasible with low additional infrastructure costs, since the model mainly relies on existing facilities and human resources. Key enabling factors include policy recognition of reuse, collaboration with system operators, targeted mentoring, and stakeholder coordination.

REUSE therefore demonstrates high transferability across Euro-MED due to its reliance on existing waste infrastructure, low implementation costs, and proven adaptability to both mature and emerging systems. It offers a scalable and socially inclusive pathway for circular economy development at regional level.

### 2.5 Target Adopters for 2027+ (4-5 organization types)

The WEEE REUSE solution can be replicated by a wide range of stakeholders operating in waste management, circular economy, and social inclusion sectors:

Municipal waste management authorities and public utility companies, for integration of reuse into collection systems and local waste strategies.

Social enterprises and reuse centres, for implementation of refurbishment, repurposing, and inclusive employment models.

Producer Responsibility Organizations (PROs) and system operators, for integration of reuse into EPR schemes and identification of reusable streams.

NGOs and civil society organizations, for community engagement, awareness-raising, and support to vulnerable groups.

SMEs and circular economy business networks, for development of reuse-based business models and market uptake of reused products.

## SECTION 3: WP2 RESULTS TABLE

### All-Territories Aggregated KPIs

| KPI | Target (All Territories) | Achieved (All Territories) | % Achievement | Range (Low-High Territory) | Data Source |
| --- | --- | --- | --- | --- | --- |
| WEEE collected (kg) | 20,000 kg | 24,486 kg | 122% | Bosnia and Herzegovina: 1,004 kg; Slovenia: 23,482 kg | WP2 Final Report WEEE REUSE |
| Number of devices collected | 20,000 items | 24,019 items | 120% | Bosnia and Herzegovina: 1,449 items; Slovenia: 22,570 items | WP2 Final Report WEEE REUSE |
| Stakeholders engaged | 20 | 20 | 100% | Bosnia and Herzegovina: 9; Slovenia: 11 | WP2 Final Report WEEE REUSE |
| Jobs created (vulnerable groups) | 10 | 18 | 180% | Bosnia and Herzegovina: 4; Slovenia: 14 | WP2 Final Report WEEE REUSE |
| Revenue generated (EUR) | 3,500 | 4,400 | 125% | Bosnia and Herzegovina only | WP2 Final Report WEEE REUSE |

*Note: Some targets were not defined in the Application Form and were therefore set during pilot preparation.*

## SECTION 4: CRITICAL SUCCESS FACTORS

### 4.1 What Worked Best

1. Integration of reuse with social inclusion

Evidence: 18 jobs created for vulnerable groups across the pilots.

For transfer: Integrate reuse activities with employment and social programmes from the start.

2. Use of existing infrastructure and systems

Evidence: Slovenia processed more than 20 tonnes with minimal additional costs.

For transfer: Build on existing waste systems and reuse centres instead of creating new ones.

3. Hands-on mentoring and business support in Bosnia and Herzegovina

Evidence: 9 businesses successfully tested reuse models and generated revenue.

For transfer: Provide continuous mentoring rather than one-off training.

### 4.2 Critical Mistakes Avoided

1. Over-reliance on complex repair processes → avoided by using deep-cleaning and simple reuse → outcome: safer and more scalable processes.

Evidence: Slovenian partners increased reuse rates without technical risk.

2. Top-down implementation without stakeholder buy-in → avoided through direct engagement → outcome: higher participation, with 20 stakeholders involved.

Evidence: strong SME participation in Bosnia and Herzegovina.

3. High-cost infrastructure approaches → avoided by using existing facilities → outcome: low-cost implementation.

Evidence: minimal indirect costs in Slovenia.

## SECTION 5: TRANSFERABILITY ASSESSMENT

### 5.1 Ideal Target Profile

The solution works best in territories with:

Urban context

Existing infrastructure

Supportive regulations

Stakeholder engagement capacity

Evidence: Slovenia, with higher system maturity, showed faster integration, while Bosnia and Herzegovina, with lower maturity, required a stronger capacity-building phase but still achieved strong results.

### 5.2 Transfer Feasibility by Territory Type

| Territory Type | Feasibility | Why (based on pilots) | Adaptation Required |
| --- | --- | --- | --- |
| Similar to pilot sites | High | Proven in Slovenia and Bosnia and Herzegovina | Minimal |
| Different socio-economic context | Medium | Lower-capacity systems require stronger preparatory support, as shown in Bosnia and Herzegovina | Capacity building needed |
| Different regulatory environment | Medium | Barriers may include taxation, collection systems, recycling facilities, and licensing rules | Policy alignment needed |
| Rural-dominant territories | Medium | Transfer is possible through local stakeholders, but logistics must be adapted | Logistics adaptation |

## SECTION 6: ENABLING CONDITIONS AND BARRIERS

### 6.1 Enabling Conditions (Must-Have / Nice-to-Have)

| Condition | Importance | Replicable? | Notes |
| --- | --- | --- | --- |
| Stakeholder cooperation (public, private, and social sectors) | Must-have | Yes | Key in all pilots |
| Access to WEEE streams | Must-have | Partial | Depends on the system |
| Basic REUSE knowledge and capacity | Must-have | Yes | Key in all pilots |
| Policy support for REUSE | Must-have | Partial | Depends on the system |

### 6.2 Main Barriers and Mitigation

| Barrier | Common to All Pilots? | Impact | Mitigation Applied |
| --- | --- | --- | --- |
| Regulatory barriers (taxation, unclear rules) | Yes | High | Policy recommendations, advocacy, and technical support in understanding rules |
| Limited access to quality WEEE | Partial | High | Partnerships with relevant stakeholders, involvement of institutions and recycling yards, and use of private collection channels |
| Low awareness and market demand | Yes | Medium | Awareness campaigns and capacity building for small businesses to better present reused products and their impact |

## SECTION 7: ADAPTATION ROADMAP FOR NEW TERRITORIES

### 7.1 Core Model (What Stays Fixed)

The core model includes four non-negotiable elements: collection of WEEE through existing channels, assessment and selection for reuse, reuse or refurbishment/repurposing, and integration with social inclusion and employment. These elements are essential and must remain unchanged because they define both the operational logic and the social value of the solution.

### 7.2 Adaptation Elements (What Changes by Context)

| Element | Core Approach | Adaptation by Territory Type |
| --- | --- | --- |
| Collection | Use existing systems | Urban: more structured channels; rural: more community-based approaches |
| Processing | Basic reuse and refurbishment | High-capacity territories: more advanced processing; low-capacity territories: simpler reuse models |
| Stakeholders | Multi-actor model | The exact mix depends on local governance, regulation, and the role of WEEE collection and management organizations |

### 7.3 Replication Timeline (Informed by WP2)

| Phase | Duration | Key Actions | Critical Success Factor |
| --- | --- | --- | --- |
| Stakeholder engagement | 1-2 months | Engage NGOs, social enterprises, small businesses, utility companies, and relevant institutions | Early buy-in and active involvement based on clearly presented shared objectives |
| Setup and training | 1-2 months | Train small businesses, NGOs, social enterprises, institutions, and decision-makers for REUSE application and policy adjustment | Inclusive approach involving all relevant stakeholders |
| Pilot implementation | 4-6 months | Plan implementation, test REUSE activities, promote results, and communicate stories to the wider public | Continuous support and effective monitoring |
| Full scale | 6+ months | Consolidate, test further, and promote the model more broadly | Realistic data and sustained coordination |
| Total | 6-12 months | — | — |

## SECTION 8: GOVERNANCE AND POLICY RECOMMENDATIONS

### 8.1 Legislation and Policy Support Needed

Integration of reuse into waste management legislation.

Removal of double taxation on reused electronics.

Incentives for social enterprises and reuse businesses.

Status: Slovenia is partially developed; Bosnia and Herzegovina requires fuller policy development.

### 8.2 Governance Structure for Multi-Stakeholder Coordination

A multi-stakeholder model is required in which:

Municipalities and authorities coordinate.

PROs manage flows.

Social enterprises implement reuse.

NGOs support awareness and implementation.

Coordination should take place through working groups or steering committees.

### 8.3 Minimum Capacity Requirements (by role)

| Role | Organization Type | Minimum Capacity | Training Hours Required | Tools Provided |
| --- | --- | --- | --- | --- |
| Coordinator | Public / NGO | 1 FTE | 20 h | Guidelines |
| Technical staff | Utility sector | 2-5 experts with complementary expertise and at least 10 years of experience | 40 h | REUSE materials, legal information, and operational guidance |
| Trainer / mentor | Business and utility sector | Strong business management experience and experience in waste management | 10-20 h | Business plan tools and related materials |

## SECTION 9: MONITORING AND EVALUATION FRAMEWORK

### 9.1 Key Indicators for Transfer

When the solution is replicated in a new territory, the following should be monitored:

| Indicator Type | Indicator Name | Target | Frequency | Data Source |
| --- | --- | --- | --- | --- |
| Output | WEEE collected for recycling and REUSE | 100 kg/month | Monthly | Collection data |
| Outcome | REUSE rate | 15% | Quarterly | Organisation reports |
| Impact | Jobs created | 3 per territory | Annual | Reports and employment documents |
| Behavior | Awareness raised | 10 posts per territory, 3 events | Annually | Press clippings, reports, photos |

### 9.2 Adaptation Notes by Territory Type

Urban territories: easier data tracking.

Rural territories: more periodic and manual tracking.

## APPENDIX: HOW THIS SHEET FEEDS D.3.4.1

This Solution Sheet provides UCPB with:

1. For the Transferability Matrix:

Sections 5-6 (target profile, feasibility, barriers) provide scoring matrix rows for the solution.

2. For the Adaptation Roadmap:

Section 7 (core model, adaptation elements, timeline) provides roadmap phases for the solution.

3. For Factsheets:

Sections 2-3 (summary and KPIs) provide the basis for a 1-page factsheet.

4. For Lessons Learned Synthesis:

Sections 4 and 8 (success factors and policy recommendations) support cross-solution learning.

5. For the Future Capitalization Proposal:

Sections 7-9 (timeline, governance, monitoring) provide input for project design.