eWAsTER Solution Sheet

D.3.4.1 Transfer Package Component

Designed for: Solution Leaders (WEEE BEHAVE, 0WEEE PROCURE, WEEE REUSE)
Maximum time investment: 2 hours per solution
Goal: Data autonomy (no PP meetings required) + sufficient coverage for transferability matrix/roadmap
Output quality: 3-page structured input → UCPB integration into D.3.4.1

SECTION 1: DOCUMENT INFORMATION

Solution Name:
0WEEE PROCURE

Solution Leader (Primary Coordinator):

Slađana Maslać, MUNICIPALITY OF NEUM

Number of Participating Territories:
2 territories/countries

Participating Partners:

- UBBSLA, Bulgaria

- Marche, Italy

- NEUM, BA (Non-implementing partner)

Sheet Version & Status:
x v1.0 Draft ☐ v2.0 CO Review ☐ v3.0 Approved

Date Completed:
22.05.2026

WP2 Final Report Reference:
WEEE PROCURE WP2 Final Report, 22 May 2026

SECTION 2: EXECUTIVE SUMMARY (300 words max)

2.1 Problem Addressed

The pilot addresses the challenges of traditional linear “purchase-use-dispose” models in public procurement, which often lack structured reuse networks. Key barriers include rigid public accounting systems, technical concerns regarding secure data sanitisation and a general lack of institutional experience with circular procurement.

2.2 Core Innovation

The solution focuses on a context-adapted circular transition via two main models: Circular Ownership in Italy, using technical schools as hubs to assess and refurbish decommissioned public IT assets and a Digital Exchange Platform (EESwap/TechSwap) in Bulgaria to facilitate the direct exchange, reuse, and recycling of equipment among municipalities and citizens.

2.3 Key WP2 Results (5 bullets, quantified)

- Devices assessed for reuse: 300 units screened (Target: 400). (Refurbishing Capacity)

- Devices refurbished or exchanged: 160 units diverted from waste (Target: 200). (Operational Efficiency)

- Stakeholder Network: 40 entities active in the reuse network (Target: 60).

- Estimated WEEE reduction: 1,500 kg of WEEE reduced (Target: 2,250 kg).

- Cost savings for users: 5,000 Eur (Target: 7,500 Eur).

2.4 Transnational Potential (2-3 sentences)

The solution is highly replicable as it uses universal components: existing public ICT stock and technical school labs. Concrete evidence of stakeholder interest is proven by the formal integration of the model into the curriculum of Technical Institutes Montani (Fermo) and Volterra Elia (Ancona), alongside the active engagement of 15 Black Sea municipalities with the digital platform.

2.5 Target Adopters for 2027+ (4-5 organization types)

Who could replicate this in a future project?

- Public administrations (national/regional/local),

- Technical and vocational school systems

- Circular economy business networks

- Repair and reuse NGOs

- Producer Responsibility Organisations (PROs).

SECTION 3: WP2 RESULTS TABLE

All-Territories Aggregated KPIs

| KPI | Target (All T.) | Achieved (All T.) | % Achievement | Range (Low-High Territory) | Data Source |
| --- | --- | --- | --- | --- | --- |
| Devices assessed for reuse | 400 units | 300 | 75% | Italy: 250 units/year Bulgaria: 50 listings | WP2 Final Report, Sec 5.1 |
| Devices refurbished or exchanged | 200 units | 160 | 80% | Bulgaria: 10 Italy: 150 | WP2 Final Report, Sec 5.1 |
| Stakeholders network | 60 entities | 40 | 67% | Italy: 20 repairers Bulgaria: 20 partners | WP2 Final Report, Sec 5.1 |
| Estimated WEEE reduction | 2.250 kg | 1,500 kg | 67% | High Bulgaria | WP2 Final Report, Bulgaria KPI |
| Cost savings for users | €7.500 | €5,000 | 67% | Bulgaria specific target | WP2 Final Report, Bulgaria KPI |
| CO2 emissions avoided | 3.75 tons | 2.5 tons | 67% | Bulgaria specific target | WP2 Final Report, Bulgaria KPI |
| Average Reuse Rate (%) | 50% | 50% | 100% | Italy: 25%–60% Bulgaria: 60% | WP2 Final Report, Sec 5.1 |

Notes:

- All data extracted directly from WP2 Final Report (date: 10-04-2026).

- Range column shows territorial variation; helps identify scalability patterns.

- Data sources traceable; no estimation.

SECTION 4: CRITICAL SUCCESS FACTORS

4.1 What Worked Best (Top 3)

- Schools as Refurbishment Hubs: Using technical and vocational institutes to assess and repair decommissioned equipment combines hands-on vocational training with social value

- Evidence: Technical institutes such as Montani (Fermo) and Volterra Elia (Ancona) successfully integrated hardware diagnostics and SSD upgrades into their curriculum, targeting a reuse rate of 25–60% for institutional PCs.

- For transfer: Future adopters should identify schools with IT/electronics specialisations and sign formal agreements to use their laboratories as "local refurbishment hubs"

- Selective Census/Interception: Identifying reusable devices at the "Dual Use" stage, after they are decommissioned but before they are formally classified as waste, maximises their "second life" potential.

- Evidence: The pilot identified an annual flow of 200–300 decommissioned units in the Marche Region. By applying a technical checklist during the initial inventory, they ensured only viable units entered the refurbishment chain.

- For transfer: Implement visual analysis and standardized technical checklists at the public procurement (Economato) level to filter equipment before it reaches waste collection points.

- Multi-Actor Governance: Establishing a structured network involving public authorities, municipalities, NGOs, and professional repairers ensures the solution is grounded in local needs.

- Evidence: The UBBSLA (Bulgaria) engaged 15 municipalities and 20 partner organisations to test the EESwap platform, while Italy formalised a directory of 20 local professional repairers to support reuse centres.

- For transfer: Designate a central regional body (e.g., Regional Authority or Municipal Association) to serve as a coordinator to bridge the gap between asset providers (public offices) and end-users.

  - Critical Mistakes Avoided (Top 3)

- Rigid Adherence to Eco-Renting.

- Mistake avoided: Proceeding with the original eco-renting/leasing concept despite legal barriers.

- Reason: Legal assessments showed that the Bulgarian Public Procurement Act and rigid Italian accounting systems (CAPEX vs. OPEX) made eco-renting unfeasible within the project timeframe.

- Outcome: The pilots pivoted to circular ownership models (Italy) and a digital exchange platform (Bulgaria), which achieved circularity goals while remaining 100% legally compliant.

- Evidence: WP2 Report Section 2.4 confirms that adapting the model to local regulatory frameworks ensured the pilot's success.

- Neglecting Data Security.

- Mistake avoided: Transferring institutional hardware without a standardised, secure data destruction protocol.

- Reason: Institutional resistance to reuse often stems from fears regarding privacy and data leaks.

- Outcome: The project established a certified data wiping and hardware destruction process (costing €10/unit) to ensure all assets were safe for redistribution.

- Evidence: Standardised data protection procedures were identified as a mandatory condition for replication in Section 5.3 of the Italian report.

- Mass Collection without Technical Filtering

- Mistake avoided: Bulk collection of all old IT equipment regardless of condition.

- Reason: Collecting obsolete or damaged "junk" hardware increases logistics costs and reduces the efficiency of refurbishment hubs.

- Outcome: By focusing only on institutional devices aged 5–7 years and using pre-selection criteria, the pilot maintained an average refurbishment cost of €140 per unit.

- Evidence: WP2 Pilot Methodology (Italy) highlights that "Selective Census" is a best practice to avoid environmental and economic liabilities.

SECTION 5: TRANSFERABILITY ASSESSMENT

5.1 Ideal Target Profile (check all that apply)

Your solution works best in territories with:

- X Urban context High concentration of public ICT assets

- X Existing school infrastructure Presence of technical/IT institutes capable of acting as hubs

- X Supportive regulations Alignment with national Minimum Environmental Criteria (CAM)

- X Stakeholder engagement capacity Regional authority willing to act as a central coordinator

Evidence from pilots: The pilot results indicate that the solution is most effective in territories with strong regional leadership and established vocational school networks, as seen in Marche, where technical institutes successfully became operational refurbishment hubs. In contexts with restrictive procurement laws, such as Bulgaria, the solution’s success relied on high stakeholder engagement capacity to pivot from asset leasing to a digital exchange platform involving 15 municipalities.

Example: Italy (90% match) achieved an annual screening flow of 250 ICT units by utilizing existing school laboratory infrastructure; Bulgaria (75% match, including rural areas) successfully engaged 20 partner organisations to facilitate digital reuse despite initial regulatory barriers to eco-renting.

5.2 Transfer Feasibility by Territory Type

| Territory Type | Feasibility | Why (based on pilots) | Adaptation Required |
| --- | --- | --- | --- |
| Similar to pilot sites | X High ☐ Med ☐ Low | Proven success in using schools as hubs (IT) and digital platforms (BG) to divert equipment from the waste stream. | Minimal: Alignment of technical checklists and data wiping protocols. |
| Different socio-economic | ☐ High X Med ☐ Low | Low-resource areas benefit most from redistributed hardware but may lack the initial budget for refurbishment components (SSDs). | Moderate: Identification of external funding or PRO sponsorship for hardware upgrades. |
| Different regulatory environment | ☐ High X Med ☐ Low | Rigid public accounting (CAPEX/OPEX) or procurement acts can block eco-renting models. | Extensive: Pivot to "Circular Ownership" or "Digital Exchange" models that work within existing laws. |
| Rural-dominant | ☐ High X Med ☐ Low | High logistical costs for device collection and fewer technical schools available as hubs. | Moderate: Adoption of the digital exchange model (TechSwap) to decentralize logistics via courier services. |

SECTION 6: ENABLING CONDITIONS & BARRIERS

6.1 Enabling Conditions (Must-Have, Nice-to-Have)

| Condition | Importance | Replicable? | Notes |
| --- | --- | --- | --- |
| Regional inventory/tracking system | X Must ☐ Nice | X Yes ☐ Partial | Essential for monitoring the flow of decommissioned ICT assets from providers to users. |
| Formal institutional agreements between authorities and schools | X Must ☐ Nice | X Yes ☐ Partial | Legal framework/MOUs between public bodies, schools, and reuse centres are vital for asset transfers. |
| Dedicated funding for initial refurbishment hardware | X Must ☐ Nice | X Yes ☐ Partial | Required for purchasing components like SSDs to ensure refurbished tech is functionally viable. |

6.2 Main Barriers & Mitigation

| Barrier | Common to All Pilots? | Impact (H/M/L) | Mitigation Applied (What Worked?) |
| --- | --- | --- | --- |
| Administrative complexity in public accounting | X Yes ☐ Partial ☐ Territory-specific | X H ☐ M ☐ L | When eco-renting proved unfeasible due to the Bulgarian Public Procurement Act and rigid Italian accounting (CAPEX/OPEX), the pilots pivoted to "Circular Ownership" and Digital Exchange Platforms |
| Logistical challenges in device collection | X Yes ☐ Partial ☐ Territory-specific | X H ☐ M ☐ L | Adopted a "Selective Census" approach, performing technical screenings at the source to prevent collecting non-reusable "junk" |
| Limited institutional experience | X Yes ☐ Partial ☐ Territory-specific | X H ☐ M ☐ L | Provided capacity building, workshops, and legal guidance for public administrators on circular procurement. |

SECTION 7: ADAPTATION ROADMAP FOR NEW TERRITORIES

7.1 Core Model (What Stays Fixed)

Core Model: (1) Selective census of decommissioned equipment, (2) Certified data wiping and technical diagnostics, (3) Refurbishment via technical hub or listing on a digital exchange platform, and (4) Social delivery to schools, NGOs, or citizens in need

7.2 Adaptation Elements (What Changes by Context)

| Element | Core Approach | Adaptation by Territory Type |
| --- | --- | --- |
| Refurbishment Infrastructure | [Standard] | Urban/High Capacity: Establish Technical Vocational Schools as "Local Refurbishment Hubs" (Italy model). Rural/Low Capacity: Use a decentralized Digital Exchange Platform (EESwap) for direct peer-to-peer municipal exchange (Bulgaria model) |
| Logistics and collection | [Standard] | Urban: Utilize centralized regional logistics and warehouses. Rural: Integrate automated courier service calculations into the digital platform for decentralized delivery |
| Stakeholder Role | [Standard] | Regulatory Supportive: Implement formal circular procurement/eco-renting tenders. Neutral/Restrictive: Pivot to a "Circular Ownership" model that transfers assets via MOUs rather than complex service contracts |

7.3 Replication Timeline (Informed by WP2)

Based on your pilot experience, how long to replicate in a new territory?

| Phase | Duration | Key Actions | Critical Success Factor |
| --- | --- | --- | --- |
| Stakeholder Engagement | 2 Months | Conduct roundtables with municipal IT departments, school directors, and repair NGOs. | Early institutional buy-in and mapping of available ICT stock. |
| Setup & Training | 2 Months | Perform legal feasibility assessment; develop the digital platform or set up school laboratory hubs. | Adapting the model to local procurement acts (e.g., Circular Ownership vs. Eco-renting). |
| Pilot Implementation | 4 Months | Start selective census of devices; perform certified data wiping and hardware refurbishment (SSD upgrades). | Adherence to standardized technical checklists and data sanitization protocols. |
| Full Scale | Ongoing | Promote platform/hub results; integrate the model into Regional Waste Prevention Plans. | Formalizing the network via regional decrees or municipal ordinances. |
| Total | 8 Months | — | — |

SECTION 8: GOVERNANCE & POLICY RECOMMENDATIONS

  - Legislation/Policy Support Needed

- [Policy 1]: Regulatory Reform of National Public Procurement Acts.

Concrete requirement: Amend national procurement legislation (such as the Bulgarian Public Procurement Act) to explicitly accommodate "Product-as-a-Service" or eco-renting models. This must clarify legal uncertainties regarding ownership, liability for maintenance, and the accounting treatment (CAPEX vs. OPEX) for public bodies when they do not own the hardware.

- [Policy 2]: Mandatory Integration of Reuse Targets in Regional Waste Plans.

Concrete requirement: Formally include specific reuse and refurbishment targets for institutional ICT assets within Regional or Local Waste Prevention Programmes. Policy should mandate that public entities screen decommissioned equipment for "Dual Use" potential (refurbishment) before it is legally classified as waste.

- [Policy 3]: Establishment of Standardized Certified Data Sanitization Protocols.

Concrete requirement: Create legally recognized, standardized procedures for certified data destruction on decommissioned institutional hardware. This removes the administrative fear of data leaks, which currently acts as a primary barrier preventing public offices from transferring assets to schools or NGOs.

- [Policy 4]: Financial Stimuli and Support Services for Circular Procurement.

Concrete requirement: Implement financial incentives for companies that exceed minimum environmental requirements in tenders and establish centralized databases for "green" requirements and eco-labels to support small municipalities.

Current status in pilot territories: [Which territories have this in place? Which need to develop it?]

- Italy (Marche): Advanced. Circular practices have already been solidified into an Action Plan within the Regional Waste Prevention Programme. Policy endorsement has been achieved where regional rules for the Purchasing Office (Economato) are aligned with the operational needs of schools for refurbishment.

- Bulgaria (Varna): Needs Development. Current legislation is restrictive; the Public Procurement Act does not yet support the original eco-renting concept. National-level regulatory adjustments and capacity building for public authorities on circular practices are required.

8.2 Governance Structure for Multi-Stakeholder Coordination

A multi-stakeholder steering committee led by a regional coordinator, comprising regional purchasing offices (asset providers), technical schools (refurbishers) and environmental agencies (policy alignment).

8.3 Minimum Capacity Requirements (by role)

| Role | Organization Type | Minimum Capacity | Training Hours Required | Tools Provided |
| --- | --- | --- | --- | --- |
| Project Coordinator | Regional Authority / Municipal Union | 0.2 – 0.5 FTE for 6–9 months | 8 – 16 hours | Pilot guidelines, technical checklists, reporting templates. |
| Technical Hub Manager | Vocational School / Technical Institute | 1 Focal point per laboratory | 8 – 12 hours | Hardware diagnostics tools, SSD upgrade kits, data wiping software. |
| Platform/Inventory Manager | Regional IT Team / Association | 0.1 FTE (Monthly oversight) | 4 – 6 hours | EESwap/TechSwap Admin Panel, User Guides. |

SECTION 9: MONITORING & EVALUATION FRAMEWORK

9.1 Key Indicators for Transfer

When your solution is replicated in a new territory, what should be monitored?

| Indicator Type | Indicator Name | Target | Frequency | Data Source |
| --- | --- | --- | --- | --- |
| Output | Number of devices assessed and collected | 250 units / year | Monthly | Regional procurement/inventory logs. |
| Outcome | Actual reuse rate (% of listed devices diverted from waste) | 40% – 60% of assessed stock | Quarterly | Refurbishment hub reports / Platform logs. |
| Impact | CO2 emissions avoided and student vocational training hours achieved | 2.5 tons CO2 eq | Annual | Lifecycle assessment calculations. |
| Behavior | Stakeholder satisfaction rate and municipal engagement level | > 80% | Biannual | Surveys of schools and municipalities |

9.2 Adaptation Notes by Territory Type

The method of data collection should be adapted based on the territorial context to ensure accuracy and minimize administrative burden:

- Urban / Centralized Territories (e.g., Marche Region model):

  - Tracking: Monitoring is best handled via a centralized regional inventory system (Economato).

  - Data Flow: Output tracking is highly feasible through existing public accounting systems, as the flow of assets is controlled by a single regional authority.

- Rural / Decentralized Territories (e.g., Varna Region model):

  - Tracking: Monitoring relies on the digital exchange platform (EESwap/TechSwap).

  - Data Flow: Automated analytics from the platform (e.g., listing counts, interaction rates, successful exchanges) should be used to track performance across multiple smaller municipalities.

- Low-Resource Territories:

  - Frequency: While monthly tracking is ideal for urban areas, quarterly or biannual tracking is recommended for rural or low-resource contexts where manual surveys may be required to verify the final social delivery of hardware

APPENDIX: HOW THIS SHEET FEEDS D.3.4.1

This Solution Sheet provides UCPB with:

- For Transferability Matrix:

  - Sections 5–6 (Target profile, feasibility, barriers) → Scoring matrix rows per solution

- For Adaptation Roadmap:

  - Section 7 (Core model, adaptation elements, timeline) → Roadmap phases per solution

- For Factsheets:

  - Sections 2–3 (Summary, KPIs) → 1-page factsheet per solution

- For Lessons Learned Synthesis:

  - Sections 4, 8 (Success factors, policy recommendations) → Cross-solution learning

- For Future Capitalization Proposal:

  - Sections 7–9 (Timeline, governance, monitoring) → Project design input