# eWAsTER Solution Sheet – WEEE BEHAVE

1. Document information

Solution Name: WEEE BEHAVE
Solution Leader / Primary Coordinator: Dr. Panayiotis Michael, Aradippou Larnaca, Cyprus (P11) 
Number of Participating Territories: 5 territories 
Participating Partners: Rethymno, Greece (P3); Varna region, Bulgaria (P7); Pian del Bruscolo area, Italy (P8); RSU Málaga, Spain (P9); Aradippou, Cyprus (P11) 
Sheet Status: consolidated working version for UCPB integration into D.3.4.1; final completion pending Aradippou KPI values [file:5]

2. Executive summary

2.1 Problem addressed

WEEE BEHAVE addresses low collection rates in municipal areas by engaging schools and households through behavior change campaigns. Across the pilots, the common issue is not the absence of collection systems, but the insufficient activation of citizens, schools, and local institutions around correct WEEE disposal and prevention practices .

The solution responds to this challenge by combining awareness, education, and collection-oriented action in schools and city-level environments. Its added value lies in using children and school communities as multipliers toward households, while connecting educational work with public authorities and authorized WEEE management channels.

2.2 Core innovation

The core innovation of WEEE BEHAVE is the integration of school-based educational activities with competition, gamification, and links to municipal or authorized collection systems. Rather than relying on information campaigns alone, the solution creates a peer-to-family communication mechanism in which pupils become active messengers of proper WEEE management .

The pilots show that this innovation is flexible in form but stable in logic. Competitions, games, workshops, school campaigns, city games, family outreach, and municipal visibility all serve the same core purpose: to convert awareness into measurable participation and, where possible, into collected WEEE .

2.3 Key WP2 results

Using the available aggregated KPI values for the five territories with reported data are: 4,218 participating students, 2,294 student engagements, 3,150 kg of WEEE collected, 171 participating classes, and 204 teachers involved. These are the values explicitly reported in the all-territories aggregation table .

KPI snapshot:

- Participating students: 4218

- Student engagements: 2294

- WEEE collected: 3150 kg

- Participating classes: 171

- Teacher involvement: 204

2.4 Transnational potential

WEEE BEHAVE has strong transnational potential because its core enabling conditions are widely available across MED territories: schools, public authorities, and some form of WEEE management structure. The pilot evidence suggests that the solution can travel well across territories when adapted in language, governance, educational format, and collection logistics rather than replicated as a rigid one-size-fits-all model [file:5].

The solution is particularly suitable for capitalization because it does not require major infrastructure investments. What it requires most is coordination capacity, educational material adapted to local audiences, and a credible institutional link between awareness activities and legal disposal routes .

2.5 Target adopters for 2027

The most suitable adopters are:

- School systems and education boards working with municipalities or regions.

- Municipal and regional waste management authorities

- Municipal associations and intermediary territorial organizations coordinating multiple schools or municipalities

- NGOs and environmental education organizations

- EPR schemes and circular economy networks interested in prevention and behavioral change actions

3. WP2 results table

| KPI | Target (all territories) | Achieved with available aggregated data | Average % | Range (Low-High Territory | Notes |
| --- | --- | --- | --- | --- | --- |
| Participating students | 500 | 4218 | 843,6% | Cyprus 120; Greece 1406 | Alla data included |
| Student engagements | 250 | 2294 | 917,6% | Cyprus 120; Greece 1517 | Alla data included |
| WEEE collected | 1000 | 3150 | 315% | Spain 65; Greece 2188 | Alla data included |
| Participating classes | 50 | 171 | 342% | Cyprus 6; Greece 99 | Alla data included |
| Teacher involvement | 50 | 204 | 408% | Cyprus 7; Greece 127 | Alla data included |

Interpretation of results

The pilots exceeded the common target values by a wide margin for school participation, student engagement, and teacher involvement, which confirms that WEEE BEHAVE is highly effective as a school-based mobilisation model. The results indicate strong educational reach and a capacity to activate large numbers of pupils and schools in different territorial settings.

Collection performance is also positive, but the revised draft suggests that local KPIs may not always have been counted with identical scope across territories. Some pilots included broader public interaction or multi-phase campaigns, while others focused on schools only, so the aggregate should be treated as a consolidated project value rather than a strictly comparable sum of identical local indicators .

4. Critical success factors and lessons learned

4.1 What worked best

- Age-appropriate educational design. Across pilots, educational activities were more effective when they were interactive, practical, and specifically tailored to children. This helped pupils understand what WEEE is, why it matters, and how to behave correctly, while also increasing retention and active participation .

- Competition and recognition. Competitions between classes or schools proved to be a strong motivational factor. They gave visibility to participation, created momentum inside schools, and helped translate environmental awareness into repeated action and engagement .

- Gamification and creative formats. Games, city activities, arts-based tasks, mascots, and playful workshop formats made the solution more memorable and transferable. These elements were not secondary decoration but central tools for behavioral activation and family outreach .

- Children as multipliers toward households. A common strength across pilots is the indirect influence of students on family behavior. Where this mechanism worked well, the campaign moved beyond the classroom and produced practical effects in household-level WEEE collection or awareness .

- Strong coordination among schools, municipalities, and waste actors. The draft repeatedly shows that the solution works best when roles are clearly assigned and coordination is maintained through dedicated liaisons, educators, or steering mechanisms. WEEE BEHAVE is therefore low-infrastructure but coordination-intensive .

4.2 Lessons learned synthesis

The most representative lessons learned across territories are:

- Educational campaigns are more effective when they are structured as repeated or organized processes rather than isolated workshops.

- Early involvement of school directors, teachers, and municipal actors is essential for implementation quality and timetable stability.

- Competitions and games are central success drivers, not optional additions.

- Family spillover is one of the most important pathways for impact, especially where the solution aims to improve real collection behavior.

- The value of the pilot cannot be judged only by kilograms collected, because regulatory conditions and campaign scope differed across territories.

- Short pilots can demonstrate activation and awareness, but not yet durable long-term behavioral change, which requires repetition and follow-up monitoring.

4.3 Main challenges to manage

The draft points to three recurrent challenges that should be addressed in future transfer:

- Organizational and scheduling constraints. School calendars, workshop timing, and municipal coordination can slow implementation unless responsibilities are defined early and communication is kept simple and regular .

- Ambiguity over accepted WEEE streams. The treatment of certain items, such as batteries or small devices, can create confusion or inconsistent collection practices. Future replication should therefore define clearly what can be collected, by whom, and under which legal conditions .

- Institutional or political fragility. Some activities may be vulnerable to local political conditions or changes in institutional support. Formal agreements and integration into annual plans are therefore important for sustainability and scale-up .

5. Transferability assessment

5.1 Ideal target profile

WEEE BEHAVE works best in territories with accessible public schools, a functioning municipal or regional waste management structure, and at least one public or intermediary actor capable of coordinating the campaign across schools and stakeholders. The draft also suggests that the presence of school infrastructure and stakeholder engagement capacity are more decisive than high levels of technical infrastructure .

The solution is not limited to dense urban territories. Although many pilots were urban or semi-urban, the Bulgaria experience shows that it can also operate across broader territorial networks, including mixed urban-rural settings, if the coordination model and school outreach structure are adapted accordingly .

5.2 Transfer feasibility by territory type

| Territory type | Feasibility | Why based on pilots | Adaptation required |
| --- | --- | --- | --- |
| Similar to pilot sites | High | The draft explicitly presents strong replication potential in Greece, Bulgaria, Italy, and Spain. | Moderate adaptation of materials, campaign design, and stakeholder roles. |
| Different socio-economic setting | High | The pilots did not explicitly test this variable. | Adapt communication, incentives, and outreach channels to local family realities. |
| Different regulatory environment | Low | The draft explicitly marks this category as low feasibility because legal conditions may restrict collection possibilities. | Strong redesign of collection channels and compliance procedures. |
| Rural-dominant territory | Medium | The draft marks rural-dominant settings as medium feasibility. | More distributed coordination and lighter reporting models are needed. |

6. Enabling conditions and barriers

6.1 Enabling conditions

| Condition | Importance | Replicable | Notes |
| --- | --- | --- | --- |
| School participation | Must-have | Yes | Present in all pilots and central to the solution model. |
| Municipality or region support | Must-have | Yes | Needed for legitimacy, continuity, and coordination. |
| Cultural fit and local acceptance | Must-have in practice | Yes | The draft flags cultural or political gaps as possible barriers if not managed. |
| Link to legal WEEE collection route | Must-have [file:5] | Partial to Yes | Especially important where public collection is regulated or restricted. |
| Dedicated coordination capacity | Must-have | Yes | A coordinator and school focal points are repeatedly implied as critical. |

6.2 Main barriers and mitigation

| Barrier | Commonality | Impact | Mitigation applied | What worked |
| --- | --- | --- | --- | --- |
| Organizational and scheduling problems | Territory-specific | Medium | Train-the-trainers logic, early scheduling, clear school contacts. | Better continuity and easier delivery. |
| Consideration of batteries as WEEE | Partial | Medium | Educational clarification and explicit guidance. | Reduced confusion and improved messaging consistency. |
| Reaction due to political issues | Territory-specific | Medium | Political or institutional action and endorsement. | Greater implementation stability. |

7. Adaptation roadmap for new territories

7.1 Core model – what stays fixed

Three elements should remain fixed in replication: school partnerships, curriculum-linked or school-based WEEE education, and games or competitions as the behavioral activation mechanism. These are the most stable common features across the pilots and the clearest transnational identity of WEEE BEHAVE .

The other fixed structural principle is the connection to a real disposal route. Even when the educational component is the most visible part, the model is stronger when it is tied to authorized collection channels and measurable operational outcomes [file:5].

7.2 Adaptation elements – what changes by context

| Element | Core approach | Adaptation by territory type |
| --- | --- | --- |
| School permanence and access | Standard school-based model | Urban contexts can scale through larger school systems; rural contexts require clustering and lighter coordination. |
| Teacher support | Standard but variable in intensity | Higher-capacity schools can take more implementation responsibility; lower-capacity schools may need more external facilitation. |
| Partnership with WEEE collection services | Standard closing-the-loop function | In supportive regulatory settings, collection can be more visible and direct; in neutral or restrictive settings, routes must be legally redesigned. |

7.3 Replication timeline informed by WP2

The revised draft suggests that a realistic first-cycle replication period is around 4 to 6 months, depending on territorial scale, regulatory conditions, and how many schools are involved. UCPB, Rethymno, and Málaga all support a model in which approximately 1 month is needed for setup and training, followed by a 2 to 4 month active implementation phase and ongoing scaling thereafter .

| Phase | Duration | Key actions | Critical success factor |
| --- | --- | --- | --- |
| Stakeholder engagement | About 1 month | Secure commitment from schools, municipality, education actors, and waste operators. | Expand to more schools, grades, or annual cycles. |
| Setup and training | About 1 month | Prepare materials, train facilitators, define school calendar, confirm logistics and KPI tracking. | Ready-made kit delivery; ASET coordination |
| Pilot implementation | About 2–4 months | Run educational activities, competitions, outreach, and collection actions. | Continuous monitoring; teacher support hotline |
| Full scale / repetition | Ongoing | Expand to more schools, grades, or annual cycles. | Transparent reporting to municipalities |
| Total to first deployment | About 5 months | — | — |

8. Governance and policy recommendations

8.1 Legislation and policy support needed

The revised draft confirms that WEEE BEHAVE scales best when awareness campaigns are institutionalized rather than left to voluntary, one-off initiatives. The most transferable policy needs across territories are the formal inclusion of WEEE awareness actions in municipal or regional waste plans, stronger links between school education and circular economy content, and formal cooperation frameworks connecting municipalities, schools, and authorized WEEE actors .

The territorial contributions are detailed and country-specific, but they converge on three broadly representative policy priorities:

- Annual or recurring WEEE awareness and collection campaigns should be embedded in municipal or regional waste planning.

- School or extracurricular frameworks should include basic WEEE education and awareness content.

- Cooperation between schools, local authorities, and EPR or authorized collection actors should be formalized through agreements, plans, or regulatory support.

8.2 Governance structure for multi-stakeholder coordination

The local contributions converge on a lightweight but structured governance model. One coordinating actor—municipality, municipal union, regional association, or similar intermediary body—should convene a steering mechanism involving school representatives, waste management actors, and where needed education authorities or expert organizations .

The most representative transnational governance model is therefore a WEEE School Steering Committee that meets at key campaign moments and is supported by simpler monthly coordination channels. This model reflects the common logic of the UCPB, UBBSLA, Rethymno, and RSU Málaga experiences, even though the specific institutional host differs by territory .

8.3 Minimum capacity requirements by role

The revised draft contains stronger territorial material for this section, making it possible to define an indicative transnational minimum model .

| Role | Organization type | Minimum capacity | Training hours | Tools provided |
| --- | --- | --- | --- | --- |
| Pilot Coordinator | Municipality, municipal union, regional association, or equivalent | Around 0.2–0.5 FTE for 4–6 months in standard pilots; higher in larger regional pilots. | About 6–12 hours. | Guidelines, KPI sheet, reporting templates, stakeholder contact list, campaign toolkit. |
| School Liaison / Teacher Coordinator | School | One focal point per school during active implementation; often around 0.1–0.2 FTE in the active phase. | About 4–8 hours. | Educational kit, family communication materials, rules, student materials. |
| Environmental Educator / Trainer | NGO, external educator, environmental organization, or support provider | Around 0.2–0.3 FTE during implementation, depending on workshop intensity. | About 6–12 hours. | Presentations, workshop materials, facilitation guides, awareness content, demonstration kits. |
| Waste Operator / Logistics Contact | Waste company, municipal waste department, or authorized operator | One operational contact during the pilot period. | About 2–4 hours. | Collection instructions, certificates, data recording sheet, recycling-centre linkage. |
| Municipal or Education Authority Support Role | Municipality or regional education authority | Around 0.05–0.1 FTE where authorization or institutional access is needed. | About 1–6 hours. | Official communication templates, compliance guidance, event support material. |

9. Monitoring and evaluation framework

9.1 Key indicators for transfer

The revised draft still leaves this section partly templated, but it clearly points to a basic transnational monitoring set centered on the indicators already used in the pilots: participating students, WEEE collected, teacher involvement, and student engagement [file:5].

| Indicator type | Indicator name | Suggested target logic | Frequency | Data source |
| --- | --- | --- | --- | --- |
| Output | Participating students | Set according to number of schools and age groups involved. | Monthly during campaign. | School attendance and workshop lists. |
| Outcome | WEEE collected | Set according to campaign format and legal collection route. | Quarterly or at campaign closure. | Waste operator certificates or municipal records. |
| Impact | Teacher involvement | Set according to number of participating classes and expected support role. | Semester or campaign closure. | School reporting and attendance records. |
| Behavior | Student engagement | Set through submissions, tasks, pledges, or active participation markers. | Final campaign review or annual cycle. | Competition records, workshop sheets, school reports. |

9.2 Adaptation notes by territory type

In stronger urban systems, monthly output tracking is feasible through school and municipal coordination. In more dispersed or lower-capacity settings, quarterly tracking may be more realistic, and qualitative evidence may need to complement numeric data. Where legal restrictions reduce collection opportunities, educational and behavioral indicators should receive greater weight so that the value of the solution is not judged only by kilograms collected .